## Milestons
Project | Finlotax
Project Lead | Vinodhini Pitchumani
Project Start Date | 2022-08-01
|  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
|  | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Milestone 1
UI/UX Design | UX Design - Wireframes
Backend Skeleton Design
DB Schema Design
Base Framework Setup
Platform Setup
Milestone 2
Admin Panel & Auth | Authentication Customer/Employee/Admin
Development | Admin Panel
User & Role Management Management
Basic Authentication
Google Authentication (Emp/client)
Milestone 3
Document Management | API Development
Blob Storage Integration
Document Preview Screen
Data Extraction Automation and
API Creation and Integration & testing
Milestone 4
Communication & | Email Notifications
Notifications | API Development
Integration & testing
Milestone 5 | Calendar Integration
Scheduling | Scheduling
API Development
Integration & testing
Milestone 6 | Dashboard - Summary
Dashboard & Reports | Admin Reports
Employee Reports
Customer Reports
Tansaction Resports
Payment Reports
Milestone 7 | UAT Release
UAT & Go-Live | Bug Fixes & Stabilization
Production Release